EVALAC I — CASE STUDY

THEORY OF CHANGE

Creciendo Juntos (Integrated Early Childhood Development)

PRIMARY TARGET GROUP

Children aged 0-3 years from families in the poorest 40% of population in 180 target municipalities

Secondary: Low-income caregivers (primarily mothers, also fathers and grandmothers)

EXTERNAL INFLUENCES

Economic conditions (recession, inflation, unemployment)

Political stability (government continuity, budget security)

Health system functionality (center staffing, supply availability)

Cultural norms (traditional parenting beliefs, gender roles)

Natural disasters and pandemics (service disruption)

LEVEL 1: INPUTS AND OUTPUTS

INPUTS (What We Invest)

Human Resources

750 community facilitators recruited from target neighborhoods

180 municipal coordinators (one per municipality)

23 state coordinators

National program management team (Dr. Mendoza + 15 staff)

Health center staff (existing, receive 2-day ECD training)

Early learning center educators and volunteers

Materials and Infrastructure

36-session parenting curriculum (printed manuals)

Play and learning materials (toys, books, art supplies)

Growth monitoring equipment (scales, measuring boards)

ASQ-3 developmental screening tools

Nutrition supplements (micronutrient packets, fortified foods)

Learning center equipment and furniture

Community spaces for parenting groups (borrowed/rented)

Systems and Coordination

Inter-ministerial coordination structure (Health, Social Development, Education)

Integrated information system (shared database)

Monitoring and evaluation system

Monthly supervision system for facilitators

Financial Resources

USD 285 million over 5 years (USD 1,140 per child per year)

OUTPUTS (What We Deliver)

Component 1: Parenting group sessions delivered over the program period (regular groups of caregivers)

Component 2: Regular home visits conducted by trained facilitators

Component 3: Monthly growth monitoring and ASQ-3 screening at health centers

Component 3: Nutrition supplements distributed to malnourished children

Component 4: Regular early learning center sessions for children and caregivers

REACH ASSUMPTIONS (Inputs → Outputs)

These assumptions must hold for inputs to successfully produce outputs:

Assumption R1: Facilitator Recruitment and Retention

ASSUMPTION: Community facilitators can be recruited from target neighborhoods, trained adequately in 3 weeks, and retained for program duration

RISKS IF VIOLATED:

-- High turnover disrupts group continuity and caregiver trust

-- Insufficient applicant pool forces hiring of less-qualified facilitators

-- Training inadequate to build facilitation skills

EVIDENCE SUPPORTING:

-- Brazil PIM successfully uses community-based facilitator model

-- Peer educator models effective when supervision strong (Aboud & Yousafzai 2015)

MONITORING:

-- Facilitator turnover rate (target: \<10% quarterly)

-- Training completion and quality scores

-- Monthly supervision coverage (target: 100%)

Assumption R2: Municipal Space Availability

ASSUMPTION: Municipalities provide accessible community spaces for parenting groups without cost

RISKS IF VIOLATED:

-- Groups cannot meet consistently

-- Families face transportation barriers to distant locations

-- Municipal bureaucracy delays or blocks access

MITIGATION:

-- Presidential mandate provides political leverage

-- Flexible space options (churches, schools, neighborhood centers)

MONITORING:

-- % of groups with consistent meeting space

-- Space-related dropout reasons (qualitative)

Assumption R3: Health System Integration Capacity

ASSUMPTION: Health centers have capacity to add growth monitoring, ASQ-3 screening, and nutrition distribution without overwhelming staff

RISKS IF VIOLATED:

-- Nurses cannot conduct developmental screening due to time constraints

-- Nutrition supplement stock-outs occur frequently

-- Health component becomes pro-forma (low quality)

EVIDENCE:

-- Chile Crece Contigo faced health system capacity challenges initially

-- Integration feasible but requires dedicated training and supervision

MONITORING:

-- Health center workload assessments

-- Stock-out rate (target: \<5% centers/month)

-- Service quality observations

Assumption R4: Inter-Ministerial Coordination Functions

ASSUMPTION: Three ministries (Health, Social Development, Education) coordinate effectively at national, state, and municipal levels

RISKS IF VIOLATED:

-- Bureaucratic silos prevent information sharing

-- Budget conflicts delay service delivery

-- Families receive fragmented services

MITIGATION:

-- Presidential authority and joint steering committee

-- Shared budget line and unified reporting

-- Dr. Mendoza has convening power

MONITORING:

-- Steering committee meeting frequency and decisions

-- Referral completion rates across ministries

-- Municipal coordinator reports on coordination

Assumption R5: Materials Procured and Distributed

ASSUMPTION: Learning materials, supplements, and equipment procured on time and distributed to municipalities without delays or diversion

RISKS IF VIOLATED:

-- Procurement delays prevent program start

-- Materials diverted or lost in supply chain

-- Families cannot practice without materials

MONITORING:

-- Procurement timelines tracked

-- Municipal inventory audits (quarterly)

LEVEL 2: CAPACITY CHANGE

IF outputs are delivered with adequate quality and fidelity, THEN caregivers develop new capabilities:

Capacity Change (What Caregivers Gain)

KNOWLEDGE

Understand developmental milestones and what to expect at each age

Know importance of first 1000 days for brain development

Recognize how children learn through interaction and play

SKILLS

Can engage in responsive interactions (pause, extend, follow child lead)

Able to create learning moments from daily activities (narrate, point out, question)

Know how to make toys from household materials

Can identify developmental delays and seek help

CONFIDENCE

Feel capable of supporting child development

Trust their ability to be a good parent despite poverty

Believe they are their child's first teacher

ACCESS TO RESOURCES

Have play materials and books available

Connected to peer network for support

Know how to access health and social services

Reduced social isolation through group participation

CHANGED BELIEFS AND MOTIVATION

Believe children learn from birth (not just age 3+)

Value responsive interaction and play over strict discipline

Prioritize child development despite competing demands

Experience emotional rewards when child responds positively

MEASUREMENT:

-- Knowledge: % identifying ≥6 developmental milestones (target: 80% vs 25% baseline)

-- Skills: Interaction quality observation scores (1-5 rubric; target: 3.5+)

-- Confidence: Self-efficacy scale (% confident; target: 75% vs 40% baseline)

-- Resources: HOME Inventory scores; peer network survey

-- Beliefs: Focus groups on changed mental models (qualitative)

CAPACITY CHANGE ASSUMPTIONS (Outputs → Capacity)

Assumption C1: Adequate Attendance and Engagement

ASSUMPTION: Enrolled caregivers attend sessions regularly and actively participate

RISKS IF VIOLATED:

-- Insufficient exposure to build knowledge and skills

-- Peer networks do not form without consistent group

-- Facilitator cannot build trust with sporadic attenders

WHY IT MIGHT FAIL:

-- Poverty pressures force caregivers to prioritize income generation

-- Childcare barriers (no one to watch other children during sessions)

-- Transportation costs or distance

-- Illness (caregiver or child)

-- Family opposition (partner or mother-in-law forbids attendance)

-- Sessions not relevant or engaging

MITIGATION:

-- Stipends help cover transportation and opportunity costs

-- Home visits maintain connection with irregular attenders

-- Flexible scheduling (evening or weekend options)

-- Peer accountability (group encourages attendance)

MONITORING:

-- Attendance rate tracked weekly

-- RED FLAG: \<60% meeting attendance criterion

-- Dropout reasons analyzed qualitatively

Assumption C2: Facilitator Quality and Fidelity

ASSUMPTION: Facilitators deliver curriculum with adequate quality - model techniques, provide practice opportunities, give constructive feedback, create safe space for sharing

RISKS IF VIOLATED:

-- Sessions become lectures without skill-building

-- Facilitators skip modules or change sequence

-- Caregivers gain information but not skills

WHY IT MIGHT FAIL:

-- Facilitator training inadequate (only 3 weeks)

-- High turnover means new facilitators lack experience

-- Supervision insufficient to correct quality problems

-- Facilitators overwhelmed by caseload (25 families)

MITIGATION:

-- Monthly supervision sessions for skill development

-- Observation and feedback (coordinators observe 10% sessions)

-- Peer learning among facilitators

MONITORING:

-- Curriculum fidelity scores (observation checklist)

-- Facilitator quality ratings (coordinator assessments)

-- Caregiver satisfaction surveys

Assumption C3: Home Visits Provide Personalized Support

ASSUMPTION: Monthly home visits effectively complement group sessions by providing context-specific coaching

RISKS IF VIOLATED:

-- Visits too brief or infrequent to observe real home dynamics

-- Facilitators cannot reach all 20-25 assigned families monthly

-- Generic advice instead of personalized coaching

WHY IT MIGHT FAIL:

-- Geography (families live far apart; travel time excessive)

-- Safety concerns in violent neighborhoods

-- Families not home when facilitator visits

MONITORING:

-- Home visit completion rate (target: 90% families/month)

-- Visit duration (target: 45-75 minutes average)

Assumption C4: Health Services Delivered with Quality

ASSUMPTION: Health center staff integrate developmental guidance into routine visits - not just weigh children but discuss milestones, demonstrate activities, provide encouragement

RISKS IF VIOLATED:

-- Health visits become transactional (weigh, record, dismiss)

-- Developmental screening administered but not explained

-- Nutrition counseling generic, not personalized

WHY IT MIGHT FAIL:

-- Nurses too busy to spend time on developmental guidance

-- 2-day training insufficient to change practice

-- Nurses lack confidence in ECD content

MONITORING:

-- Observation of health visits (quality scoring)

-- Caregiver reports of guidance received

Assumption C5: Learning Centers Provide Demonstration Value

ASSUMPTION: Early learning centers effectively demonstrate age-appropriate activities that caregivers can replicate at home

RISKS IF VIOLATED:

-- Centers seen as childcare, not learning models

-- Activities too complex or resource-intensive for home replication

MONITORING:

-- Center attendance rates

-- Caregiver reports of trying activities at home

LEVEL 3: BEHAVIOR CHANGE

IF caregivers gain knowledge, skills, confidence, resources, and changed beliefs, THEN they change daily parenting behaviors:

Behavior Changes (Observable Actions)

INCREASED RESPONSIVE INTERACTION TIME:

-- Daily minutes in responsive interaction increases

-- Caregivers talk to children during daily activities (cooking, bathing, walking)

-- Narrate actions, point out colors/shapes/numbers in environment

IMPROVED INTERACTION QUALITY:

-- Follow child lead in play rather than directing

-- Pause after speaking to give child time to respond

-- Extend child utterances (child says \"car\" → caregiver says \"yes, red car going fast\")

-- Make eye contact and show positive affect

POSITIVE DISCIPLINE REPLACES HARSH PUNISHMENT:

-- Use redirection and guidance instead of yelling or hitting

-- Explain consequences calmly

-- Recognize child emotions and help regulate

ENRICHED HOME LEARNING ENVIRONMENT:

-- Books and toys visible and accessible

-- Designated play space created despite crowding

-- Safety improvements (cover outlets, remove hazards)

ACTIVE PEER SUPPORT SEEKING:

-- Regular contact with 3+ program peers outside sessions

-- Share challenges and solutions

-- Mutual encouragement and accountability

MEASUREMENT:

-- Interaction time: Time-use surveys (baseline, M6, M12, M18)

-- Interaction quality: Observation during home visits (1-5 rubric)

-- Discipline: Discipline practices survey (Conflict Tactics Scale)

-- Home environment: HOME Inventory scores

-- Peer support: Social network surveys

BEHAVIOR CHANGE ASSUMPTIONS (Capacity → Behavior)

These assumptions explain why and under what conditions increased capacity translates into actual behavior change in daily life.

Assumption B1: Knowledge and Skills Translate to Daily Practice

ASSUMPTION: Gaining knowledge in sessions and practicing skills with facilitator leads caregivers to actually change how they interact with children at home every day

RISKS IF VIOLATED:

-- Caregivers know what to do but do not do it

-- Behavior change remains in \"performance mode\" (only during visits) rather than becoming habitual

WHY KNOWING ≠ DOING:

-- Poverty stress and exhaustion override intention

-- Family opposition blocks practice (partner ridicules, grandmother forbids)

-- Lack of time (competing demands from work, chores, other children)

-- Lack of intrinsic motivation (doing it because told, not because valued)

-- Old habits strong and automatic

CONDITIONS THAT HELP TRANSLATION:

-- Peer group normalizes new practices (social proof)

-- Caregiver experiences emotional rewards quickly (child smiles, responds)

-- Home visits provide accountability and encouragement

-- New identity forms (\"I am my child first teacher\")

EVIDENCE:

-- Behavior change literature: intention-behavior gap well documented

-- Need opportunity + motivation alongside capability (COM-B framework)

MONITORING:

-- Correlation between knowledge scores and observed behavior

-- Qualitative exploration of barriers to practice

Assumption B2: Peer Networks Provide Sustained Support

ASSUMPTION: Peer networks formed in parenting groups continue to function after sessions end, providing ongoing emotional support, practical advice, and accountability

RISKS IF VIOLATED:

-- Isolation returns after program ends

-- No one to ask questions or share challenges with

-- Behavior change fades without peer reinforcement

WHY NETWORKS MIGHT NOT FORM:

-- Geographic distance (live far apart)

-- Socioeconomic differences create barriers

-- Lack of trust or personal conflicts

-- No communication infrastructure (no phones, no WhatsApp)

MONITORING:

-- % with active peer network (≥3 contacts/month)

-- Network persistence at Month 18 (after program ends)

Assumption B3: Materials Accessible and Used

ASSUMPTION: Distributed materials (books, toys) remain accessible and are actually used regularly

RISKS IF VIOLATED:

-- Materials sold or traded due to poverty pressures

-- Books stored away \"to keep nice\" rather than used daily

-- Toys broken quickly without replacements

MONITORING:

-- HOME Inventory during home visits (materials visible?)

-- Qualitative reports of material use

Assumption B4: Changed Beliefs Persist Under Pressure

ASSUMPTION: Changed beliefs about parenting persist even when caregivers face poverty stress, family opposition, or exhaustion

RISKS IF VIOLATED:

-- Revert to traditional practices under stress

-- Grandmother or partner pressure overrides new beliefs

CONDITIONS FOR PERSISTENCE:

-- Beliefs internalized (intrinsic not extrinsic motivation)

-- Visible results reinforce beliefs (child clearly developing better)

MONITORING:

-- Belief surveys at M12 and M18

-- Qualitative on sustaining practices under adversity

Assumption B5: Time Protected for Interaction

ASSUMPTION: Caregivers can protect 30-45 daily minutes for responsive interaction despite competing demands (work, chores, other children, exhaustion)

RISKS IF VIOLATED:

-- Intention to interact but no time actually available

-- Exhaustion prevents quality interaction

MITIGATION:

-- Teach integration into daily activities (not separate \"teaching time\")

-- Brief moments count (5-10 min several times/day)

MONITORING:

-- Time-use surveys

-- Qualitative on time barriers

LEVEL 4: DIRECT OUTCOMES (Child Development)

IF caregivers change their daily interactions - increasing quantity, improving quality, using positive discipline, enriching environment - THEN children show developmental gains:

Child Development Outcomes (6-24 Months)

LANGUAGE DEVELOPMENT:

-- Increased vocalizations (babbling, attempting words)

-- Vocabulary growth (more words understood and produced)

-- Sentence complexity increases

MOTOR DEVELOPMENT:

-- Gross motor: crawling, walking, running, climbing milestones

-- Fine motor: grasping, manipulating objects, drawing

SOCIAL-EMOTIONAL DEVELOPMENT:

-- Secure attachment (child seeks caregiver when distressed)

-- Emotion regulation improves (less tantrums, calms faster)

-- Social engagement (eye contact, smiling, showing objects)

COGNITIVE DEVELOPMENT:

-- Problem-solving skills (figuring out how toys work)

-- Attention and persistence increase

-- Curiosity and exploration

OVERALL DEVELOPMENTAL STATUS:

-- TARGET: 65% of children achieve age-appropriate development on ASQ-3 all domains by Month 24 (vs 35% baseline)

Nutritional Status (for Malnourished Children)

Weight-for-age, height-for-age, weight-for-height z-scores improve

TARGET: 50% of malnourished children show ≥0.5 SD improvement by Month 12

Caregiver Well-Being (Secondary Outcomes)

Parenting stress reduces (Parenting Stress Index scores)

Depressive symptoms decrease (where elevated at baseline)

Parenting satisfaction increases

MEASUREMENT:

-- ASQ-3 developmental screening (baseline, M12, M24)

-- Domain-specific assessments (language, motor, social-emotional)

-- Anthropometric measurements (monthly at health centers)

-- Caregiver stress and mental health scales

DIRECT OUTCOME ASSUMPTIONS (Behavior → Outcomes)

Assumption O1: Sufficient Dosage and Quality

ASSUMPTION: The amount and quality of changed caregiver-child interaction is sufficient to produce detectable developmental gains

RISKS IF VIOLATED:

-- Interaction time increases but quality poor (mechanical, not responsive)

-- Quality improves but time too brief (5 min/day insufficient)

-- Effects too small to detect with available measures

WHAT CONSTITUTES \"SUFFICIENT\"?

-- Evidence: Colombia showed 0.22-0.26 SD gains with intensive program

-- Jamaica showed larger gains but with weekly visits over 2 years

-- Our dosage: 9 months + monthly home visits = moderate intensity

MONITORING:

-- Interaction quantity (time-use) AND quality (observations)

-- Correlation: Does interaction time/quality predict child outcomes?

Assumption O2: No Overwhelming Competing Adversities

ASSUMPTION: While families face poverty, most do not experience adversities so severe that improved parenting alone cannot produce developmental gains

RISKS IF VIOLATED:

-- Severe food insecurity (child malnourished despite supplements)

-- Untreated health problems (chronic illness, disabilities)

-- Exposure to violence (witnessing or experiencing)

-- Major family disruption (parent incarceration, domestic violence, displacement)

-- Toxic stress overwhelms protective factors

WHY THIS MATTERS:

-- Parenting is NECESSARY but may not be SUFFICIENT under extreme adversity

-- Integrated approach (Component 3 nutrition) helps but cannot solve everything

EVIDENCE:

-- Cumulative risk literature: multiple adversities compound effects

-- PIM Brazil study: effects under \"regular conditions\" shows resilience

MONITORING:

-- Track external shocks (economic crisis, family events)

-- Heterogeneity analysis: outcomes by adversity severity

Assumption O3: Developmental Gains Specific to Stimulation

ASSUMPTION: Developmental improvements are concentrated in domains most responsive to stimulation (language, social-emotional, cognitive) rather than uniform gains

WHY THIS MATTERS:

-- Validates mechanism - language should improve MOST given focus on interaction

-- If all domains improve equally, suggests alternative explanation (e.g., nutrition alone)

EVIDENCE:

-- Pakistan factorial trial: stimulation and nutrition work via different pathways

-- Colombia: language domains showed strongest effects

MONITORING:

-- ASQ-3 domain-specific scores

-- Expect language \> social-emotional \> motor

Assumption O4: Effects Emerge on Expected Timeline

ASSUMPTION: Developmental gains become detectable by Month 12 and strengthen by Month 24

WHY TIMING MATTERS:

-- Behavior change needs months to consolidate before child outcomes appear

-- If outcomes appear before behavior change, challenges ToC

-- If no outcomes by M24, dosage or mechanism problem

EXPECTED SEQUENCE:

-- M0-5: Capability building

-- M6-9: Behavior change consolidates

-- M9-12: Early child outcomes detectable (language especially)

-- M12-24: Effects strengthen and spread across domains

MONITORING:

-- Developmental assessments at M12 and M24

-- Test whether sequence matches expectation

Assumption O5: Gains Maintained or Increase Over Time

ASSUMPTION: Developmental improvements persist through Month 24 and beyond; no fade-out when program ends at Month 9

RISKS OF FADE-OUT:

-- Behavior change not internalized; reverts after program support ends

-- Peer networks dissolve

-- Family opposition increases without facilitator support

CONDITIONS FOR PERSISTENCE:

-- Intrinsic motivation (doing it because valued, not because told)

-- New practices become habitual

-- Visible child progress reinforces continued practice

EVIDENCE:

-- Colombia 2-year follow-up: effects sustained, no fade-out

-- Jamaica: effects persisted 20 years

MONITORING:

-- Behavior assessed at M18 (9 months post-program)

-- Child development at M24 (15 months post-program)

LEVEL 5: IMPACT (Long-Term - 3-5 Years)

IF developmental gains are sustained through early childhood, THEN children enter school ready to learn and succeed:

School Readiness (Age 5-6)

Children meet school readiness benchmarks

-- Pre-literacy: Recognize letters, understand print concepts, phonological awareness

-- Pre-numeracy: Count, recognize numbers, one-to-one correspondence

-- Social-emotional: Follow instructions, take turns, manage frustration, interact with peers

-- Attention and engagement: Sit for short periods, complete tasks, ask questions

Early Academic Success (Grades 1-3)

Improved literacy and numeracy in early grades

Lower first-grade retention rates (target: 50% reduction)

Better school attendance and engagement

Intergenerational Effects ASSUMPTION: Caregiver behavioral changes generalize beyond the target child to subsequent children and community networks

Caregivers apply learned practices to younger siblings

Shared knowledge with other families in community (spillover effects)

Caregivers become advocates for early childhood development

MEASUREMENT:

-- School readiness assessments at age 6

-- School administrative data (retention, attendance, grades)

-- Teacher reports on student preparation

IMPACT ASSUMPTIONS (Direct Outcomes → Impact)

Assumption I1: Gains Persist Through School Entry

ASSUMPTION: Developmental advantages maintained through ages 3-6 despite lack of continued program support

RISKS IF VIOLATED:

-- Early gains fade before school entry

-- Children \"catch down\" to baseline by age 6

WHY FADE-OUT MIGHT OCCUR:

-- Lack of quality pre-kindergarten programs (ages 3-5 unstimulating)

-- Economic shocks force families into crisis mode

-- Caregiver practices erode over years without reinforcement

MITIGATION:

-- Link families to pre-K programs

-- Peer networks provide some ongoing support

EVIDENCE:

-- Jamaica: Gains persisted through school and into adulthood

-- Colombia: Gains sustained at 2-year follow-up

-- But: Many ECD programs DO show fade-out; not automatic

MONITORING:

-- Follow cohort through age 6 (school entry)

-- School readiness assessments

Assumption I2: School Quality Adequate

ASSUMPTION: Primary schools provide adequate quality instruction (EXTERNAL CONDITION, outside program control --- affects whether developmental gains translate to academic achievement)

RISKS IF VIOLATED:

-- Schools so poor that even prepared children cannot learn

-- Teachers unprepared to build on child readiness

-- Large class sizes prevent individual attention

WHY THIS MATTERS:

-- School readiness is necessary but not sufficient without decent schools

-- If school quality terrible, early advantages may not translate to achievement

MITIGATION:

-- Advocate for primary education quality improvements (beyond program scope)

MONITORING:

-- Track school quality indicators (teacher qualifications, class size, resources)

-- Heterogeneity: Do effects vary by school quality?

Assumption I3: Family Circumstances Stable Enough

ASSUMPTION: Most families maintain relative stability through child primary school years (no major disruptions like migration, displacement, family breakdown)

RISKS IF VIOLATED:

-- Forced migration disrupts schooling

-- Economic crisis forces child labor

-- Family dissolution (separation, incarceration) creates trauma

MONITORING:

-- Track family stability in follow-up surveys

Assumption I4: Early Advantages Cumulative Not Fleeting

ASSUMPTION: Early developmental gains create cumulative advantages (better child performance → more teacher attention → faster learning → more confidence) rather than one-time boosts

EVIDENCE:

-- Developmental cascade literature: early skills scaffold later skills

MONITORING:

-- Track achievement trajectories (not just point-in-time)

-- Test whether gaps widen, stable, or narrow over time