EVALAC I — CASE STUDY

OPERATIONAL MONITORING SYSTEM

Creciendo Juntos (Integrated Early Childhood Development)

OPERATIONAL MONITORING SYSTEM

The monitoring system serves three purposes: (1) operational management - identifying and resolving implementation problems quickly, (2) learning and adaptation - understanding what works and what does not, and (3) contribution analysis - generating evidence to assess program contribution to observed outcomes.

The system is designed around realistic assessment of what can actually be measured given budget constraints, staff capacity, and bureaucratic systems. It avoids monitoring everything poorly in favor of monitoring key signals well.

MONITORING FRAMEWORK: THREE TIERS

TIER 1: Implementation Fidelity (Are we delivering as designed?)

PURPOSE: Ensure program implemented as designed; identify problems quickly

PRIMARY USERS: Municipal coordinators, state coordinators, national program management

FREQUENCY: Real-time to monthly

TIER 2: Mechanism Tracking (Is the ToC working?)

PURPOSE: Test whether expected causal pathways (COM-B) actually function; validate or challenge assumptions

PRIMARY USERS: Evaluation team, program management for adaptation

FREQUENCY: Baseline, midline (Month 9), endline (Month 18-24)

TIER 3: Outcome Measurement (Are results appearing?)

PURPOSE: Assess whether child development, parenting practices, family well-being improve

PRIMARY USERS: Evaluation team, decision-makers (President, Congress, Treasury)

FREQUENCY: Baseline, interim (Month 12), endline (Month 24), follow-up (36-60 months)

TIER 1: IMPLEMENTATION FIDELITY MONITORING

A. Coverage and Reach Indicators

PURPOSE: Track whether program reaching intended beneficiaries

Indicator 1.1: Municipal Coverage

DEFINITION: % of 180 target municipalities with active parenting groups operating

DATA SOURCE: Program dashboard (municipal coordinators report weekly)

FREQUENCY: Monthly aggregation

BASELINE: 0%

TARGET: 100% by Month 6; maintain 95%+ thereafter

MANAGEMENT USE: Identify municipalities falling behind; trigger technical assistance

RED FLAG: \<90% coverage for 2 consecutive months

Indicator 1.2: Family Enrollment

DEFINITION: Number of families enrolled vs target of 50,000

DATA SOURCE: Enrollment database (municipal coordinators enter data)

FREQUENCY: Monthly cumulative total

BASELINE: 0

TARGET: 15,000 by Month 6; 35,000 by Month 12; 50,000 by Month 18

MANAGEMENT USE: Track progress toward coverage goals; adjust recruitment strategies

RED FLAG: \>10% behind target trajectory

Indicator 1.3: Socioeconomic Targeting

DEFINITION: % of enrolled families from poorest quintile (primary target)

DATA SOURCE: Enrollment forms (caregivers self-report income, assets); cross-check with social registry

FREQUENCY: Quarterly assessment

BASELINE: N/A

TARGET: ≥70% from poorest 40% of population

MANAGEMENT USE: Assess targeting accuracy; adjust outreach if reaching wrong families

RED FLAG: \<60% from target population

Indicator 1.4: Geographic Distribution

DEFINITION: Enrollment distribution across urban/peri-urban/rural municipalities

DATA SOURCE: Enrollment database with municipality type flag

FREQUENCY: Quarterly

TARGET: Proportional to population distribution in target areas

MANAGEMENT USE: Identify geographic biases; ensure peri-urban/rural not underserved

B. Service Delivery Indicators (Outputs)

PURPOSE: Track whether intended services actually delivered

Indicator 1.5: Parenting Sessions Delivered

DEFINITION: Average number of sessions delivered per group (target: 36 over 9 months)

DATA SOURCE: Facilitator activity reports (weekly submission, monthly aggregation)

FREQUENCY: Monthly average across all groups

BASELINE: 0

TARGET: 4 sessions/month average (36 over 9 months)

MANAGEMENT USE: Identify facilitators/municipalities falling behind schedule

RED FLAG: \<3 sessions/month for 2+ consecutive months

Indicator 1.6: Caregiver Attendance Rate

DEFINITION: % of enrolled caregivers attending ≥70% of sessions (minimum for adequate exposure)

DATA SOURCE: Attendance sheets (facilitators record; entered weekly)

FREQUENCY: Monthly calculation

BASELINE: N/A

TARGET: ≥75% attend ≥70% of sessions

MANAGEMENT USE: Early warning of engagement problems; identify high-dropout groups for intervention

RED FLAG: \<60% attendance rate

Indicator 1.7: Average Group Size

DEFINITION: Average number of caregivers per active group

DATA SOURCE: Attendance records aggregated

FREQUENCY: Monthly

TARGET: 12-15 caregivers per group (optimal for interaction)

MANAGEMENT USE: Identify groups too large (split) or too small (merge/recruit)

RED FLAG: \<8 or \>20 caregivers per group

Indicator 1.8: Home Visits Delivered

DEFINITION: % of enrolled families receiving monthly home visits as designed

DATA SOURCE: Facilitator logs (visit date, duration, family ID)

FREQUENCY: Monthly

TARGET: ≥90% of families receive visit each month

MANAGEMENT USE: Identify overloaded facilitators; assess visit feasibility

RED FLAG: \<75% families visited in a month

Indicator 1.9: Home Visit Duration

DEFINITION: Average duration of home visits (target: 60 minutes)

DATA SOURCE: Facilitator logs; monthly sample audit (coordinators observe 10% of visits)

FREQUENCY: Monthly sample

TARGET: 45-75 minutes average (some flexibility for family circumstances)

MANAGEMENT USE: Ensure visits not too brief (ineffective) or too long (unsustainable)

Indicator 1.10: Facilitator Supervision Coverage

DEFINITION: % of facilitators receiving monthly supervision sessions

DATA SOURCE: Municipal coordinator records

FREQUENCY: Monthly

TARGET: 100% facilitators supervised monthly

MANAGEMENT USE: Ensure supervision system functioning; identify coordinator capacity issues

RED FLAG: \<85% supervision coverage

Indicator 1.11: Growth Monitoring Coverage

DEFINITION: % of enrolled children receiving monthly growth monitoring at health centers

DATA SOURCE: Health center records (matched to enrollment database)

FREQUENCY: Monthly

TARGET: ≥85% children monitored monthly

MANAGEMENT USE: Assess health system integration; identify access barriers

RED FLAG: \<70% coverage

Indicator 1.12: Nutrition Supplement Stock-Out Rate

DEFINITION: % of health centers experiencing stock-outs of nutrition supplements in a given month

DATA SOURCE: Health center inventory reports

FREQUENCY: Monthly

TARGET: \<5% centers with stock-outs

MANAGEMENT USE: Supply chain management; prevent service disruption

RED FLAG: \>15% centers with stock-outs

Indicator 1.13: Learning Center Attendance

DEFINITION: Average attendance at twice-weekly learning center sessions

DATA SOURCE: Center attendance logs (weekly → monthly aggregation)

FREQUENCY: Monthly

TARGET: ≥60% of enrolled families attend ≥1 session/week

MANAGEMENT USE: Assess center utilization; adjust schedules/locations if low

C. Quality and Fidelity Indicators

PURPOSE: Assess not just delivery but quality of implementation

Indicator 1.14: Curriculum Fidelity

DEFINITION: % of observed sessions covering required curriculum elements (checklist)

DATA SOURCE: Structured observations by coordinators (10% of sessions/month sampled)

FREQUENCY: Monthly sample

TARGET: ≥80% of observed sessions meet fidelity criteria

MANAGEMENT USE: Identify training needs; ensure curriculum integrity

Indicator 1.15: Facilitator Turnover Rate

DEFINITION: % of facilitator positions experiencing turnover (resignation/termination) in a 3-month period

DATA SOURCE: HR records

FREQUENCY: Quarterly

TARGET: \<10% quarterly turnover (40% annual is concerning)

MANAGEMENT USE: Assess retention; improve working conditions if high turnover

RED FLAG: \>15% quarterly turnover

TIER 2: MECHANISM TRACKING (COM-B)

PURPOSE: Test whether expected causal pathways actually function; validate ToC assumptions

A. Capability Indicators

RESEARCH QUESTION: Are caregivers gaining knowledge, skills, and confidence?

Indicator 2.1: Developmental Milestone Knowledge

DEFINITION: % of caregivers correctly identifying ≥6 developmental milestones from list of 10

DATA SOURCE: Structured knowledge survey (evaluator-administered)

SAMPLE: Representative sample of 600 caregivers (treatment), 400 comparison

FREQUENCY: Baseline (before program), Month 5 (mid-program), Month 9 (end-program)

BASELINE EXPECTATION: 25% (from diagnostic research)

TARGET: 80% by Month 9 (treatment); 30% comparison (small natural increase)

ANALYSIS: Treatment vs comparison; dose-response (attendance → knowledge)

CONTRIBUTION EVIDENCE: If treatment \>\> comparison, supports capability mechanism

Indicator 2.2: Parenting Self-Efficacy

DEFINITION: % reporting increased confidence in supporting child development (5-point scale; \"confident\" = 4-5)

DATA SOURCE: Parenting self-efficacy scale (survey)

SAMPLE: Same 600 treatment, 400 comparison

FREQUENCY: Baseline, Month 9, Month 18

BASELINE: 40% confident

TARGET: 75% confident by Month 9 (treatment); 45% comparison

CONTRIBUTION EVIDENCE: Confidence increases AND correlates with knowledge → capability pathway validated

Indicator 2.3: Interaction Quality (Observed)

DEFINITION: Average score on home visit interaction quality rubric (1-5 scale; dimensions: responsiveness, language complexity, positive affect, follow-child-lead)

DATA SOURCE: Structured observations during home visits (facilitators rate using standardized rubric)

SAMPLE: All families receiving home visits (monthly ratings on rotating 30 families/month sample)

FREQUENCY: Monthly sample observations aggregated quarterly

BASELINE: 2.1 (from pilot observations)

TARGET: 3.5+ by Month 9

ANALYSIS: Track improvement trajectory; correlate with attendance

CONTRIBUTION EVIDENCE: Quality improves over time; higher for high-attendance families

B. Opportunity Indicators

RESEARCH QUESTION: Are caregivers gaining access to resources and social support?

Indicator 2.4: Peer Network Formation

DEFINITION: % reporting regular contact (≥1x/month) with ≥3 program peers outside formal sessions

DATA SOURCE: Social network survey

SAMPLE: 600 treatment, 400 comparison

FREQUENCY: Baseline (expect \~0%), Month 9, Month 18 (test persistence)

TARGET: 70% with active peer network by Month 9; 60% maintained at Month 18

CONTRIBUTION EVIDENCE: Networks form in treatment, not comparison; persist after program

Indicator 2.5: Home Learning Environment

DEFINITION: % of homes showing visible learning environment improvements (HOME Inventory checklist: books present, toys accessible, designated play space, safety improvements)

DATA SOURCE: HOME Inventory checklist (facilitators observe during home visits)

SAMPLE: All families receiving visits (quarterly assessments)

FREQUENCY: Baseline, Month 6, Month 12

BASELINE: 15% homes with adequate learning environment

TARGET: 65% by Month 12

CONTRIBUTION EVIDENCE: Environment improves; correlates with participation intensity

C. Motivation Indicators

RESEARCH QUESTION: Are caregivers changing beliefs and experiencing rewards?

Indicator 2.6: Changed Beliefs About Parenting (Qualitative)

DEFINITION: Thematic analysis of expressed beliefs about child development, parenting role, learning

DATA SOURCE: Focus group discussions (8-10 caregivers per group; 12 groups/wave)

FREQUENCY: Month 6, Month 12

ANALYSIS: Code for themes - \"children learn from birth,\" \"I am my child first teacher,\" \"play is learning,\" \"responsive interaction matters\"

TARGET: Themes shift from traditional beliefs to program-aligned beliefs

CONTRIBUTION EVIDENCE: Belief change narratives reference program content; contrast with comparison group

Indicator 2.7: Child Development as Life Priority

DEFINITION: % reporting child development among top 3 life priorities (open-ended then categorized)

DATA SOURCE: Survey

SAMPLE: 600 treatment, 400 comparison

FREQUENCY: Baseline, Month 9

CONTRIBUTION EVIDENCE: Priority ranking increases in treatment more than comparison

Indicator 2.8: Enjoyment of Interaction

DEFINITION: % reporting they \"enjoy\" or \"very much enjoy\" interacting/playing with child (proxy for intrinsic motivation)

DATA SOURCE: Survey (5-point scale)

FREQUENCY: Baseline, Month 9, Month 18

CONTRIBUTION EVIDENCE: Enjoyment increases; mediates relationship between program and sustained behavior

TIER 3: OUTCOME MEASUREMENT

A. Short-Term Outcomes (6-12 Months)

Outcome 1: Responsive Interaction Time

DEFINITION: Daily minutes spent in responsive interaction with child (talking, playing, reading, singing)

DATA SOURCE: Time-use survey (structured recall of previous day activities)

SAMPLE: 600 treatment, 400 comparison

FREQUENCY: Baseline, Month 6, Month 12

BASELINE: 15 minutes/day average

TARGET: 45+ minutes/day by Month 12 (treatment); 20 minutes comparison

ANALYSIS: Treatment effect; dose-response; mediation by COM-B indicators

Outcome 2: Positive Discipline Practices

DEFINITION: % using primarily positive discipline (guidance, redirection, natural consequences) vs harsh punishment (yelling, hitting)

DATA SOURCE: Discipline practices survey (Conflict Tactics Scale adapted)

FREQUENCY: Baseline, Month 9

BASELINE: 35% positive discipline

TARGET: 70% positive discipline (treatment); 40% comparison

Outcome 3: Nutritional Status Improvement (for Malnourished Children)

DEFINITION: % of children identified as malnourished at baseline showing z-score improvement ≥0.5 SD

DATA SOURCE: Health center anthropometric measurements

SAMPLE: All children with baseline malnutrition (estimated 28% of enrolled)

FREQUENCY: Monthly measurements, analyzed at 6 and 12 months

TARGET: 50% show meaningful improvement by Month 12

B. Medium-Term Outcomes (12-24 Months)

Outcome 4: Child Developmental Status

DEFINITION: % achieving age-appropriate development across ASQ-3 domains (communication, gross motor, fine motor, problem-solving, personal-social)

DATA SOURCE: ASQ-3 screening (administered by trained data collectors)

SAMPLE: 600 treatment children, 400 comparison

FREQUENCY: Baseline, Month 12, Month 24

BASELINE: 35% age-appropriate overall development

TARGET: 65% age-appropriate by Month 24 (treatment); 40% comparison

ANALYSIS: Overall score + domain-specific; heterogeneity by caregiver education, baseline severity

Outcome 5: Caregiver Stress

DEFINITION: Parenting stress scores (Parenting Stress Index short form)

DATA SOURCE: Survey

FREQUENCY: Baseline, Month 12, Month 24

TARGET: 35% reduction in stress scores (treatment); 10% comparison

Outcome 6: Caregiver Mental Health

DEFINITION: Depression and anxiety symptom scores (PHQ-9, GAD-7 screening tools)

FREQUENCY: Baseline, Month 12, Month 24

TARGET: 30% reduction in symptoms among those with elevated baseline

C. Long-Term Outcomes (3-5 Years) - Requires Longitudinal Tracking

Outcome 7: School Readiness

DEFINITION: % meeting school readiness benchmarks at age 6 (teacher assessments using standardized tool + school enrollment records)

SAMPLE: Cohort followed through school entry

FREQUENCY: Age 6 assessment

TARGET: 75% ready (treatment); 45% comparison areas

Outcome 8: Early Academic Performance

DEFINITION: 1st and 3rd grade literacy and numeracy scores

DATA SOURCE: School administrative data + standardized assessments

FREQUENCY: Annual

ANALYSIS: Treatment areas vs comparison areas (aggregate-level)

Outcome 9: Grade Retention

DEFINITION: % repeating first grade

TARGET: 50% reduction vs comparison areas

DATA COLLECTION METHODS AND QUALITY ASSURANCE

Quantitative Surveys

ADMINISTERED BY: Independent evaluation firm (not program staff to avoid bias)

SAMPLE: Probability sample of 600 treatment families, 400 comparison families from similar municipalities without program

MODE: Face-to-face interviews (60-90 minutes)

LANGUAGE: Local languages; translated and back-translated instruments

TRAINING: 2-week enumerator training; inter-rater reliability checks; practice interviews

QUALITY: 10% re-interviews; GPS verification of household; audio recording (with consent)

Administrative Data

SOURCES: Facilitator reports, health center records, enrollment database, learning center logs

VALIDATION: Monthly 10% spot-checks by supervisors; cross-checks between sources

DATA ENTRY: Standardized forms; validation rules in database; double-entry for key fields

QUALITY REPORTS: Monthly data quality dashboards (completeness, consistency, timeliness)

Qualitative Data

FOCUS GROUPS: 12 groups per wave (6-8 participants each); facilitator guides; audio recorded and transcribed

INTERVIEWS: Semi-structured interviews with municipal coordinators (quarterly), facilitators (monthly sample), health staff (semi-annual)

OBSERVATIONS: Structured observation tools with rubrics; observer training; inter-rater reliability ≥80%

ANALYSIS: Thematic coding using NVivo; dual coders with consensus resolution

Comparison Group Strategy

NON-RANDOMIZED: Program not randomized (all target areas receive program)

COMPARISON APPROACH: Select 60 similar municipalities not in program (matched on poverty, development indicators, geography)

PURPOSE: Assess secular trends, provide context for treatment outcomes

LIMITATION: Not counterfactual; contribution analysis does not rely solely on comparison but uses multiple evidence sources

DATA USE AND REPORTING

For Municipal Coordinators (Monthly)

DASHBOARD: Coverage, attendance, session delivery, home visit completion

RED FLAGS: Automated alerts when indicators drop below thresholds

USE: Identify struggling facilitators; adjust schedules; troubleshoot barriers

For State Coordinators (Quarterly)

REPORTS: Municipal performance comparison; facilitator turnover; quality scores

USE: Target technical assistance; recognize high performers; address systemic issues

For National Program Management (Quarterly)

REPORTS: Aggregate trends across all municipalities; mechanism indicator results; early outcome signals

USE: Assess program functioning; adapt training/curriculum; make operational decisions

For Steering Committee (Semi-Annually)

REPORTS: Progress toward targets; evidence of mechanism functioning; outcome trajectories

USE: Strategic decisions; course corrections; budget allocation

For President and Congress (Semi-Annually)

PUBLIC REPORTS: Families reached, services delivered, preliminary results, challenges encountered, adaptive responses

USE: Transparency; accountability; inform scale-up decisions

For Independent Evaluators (Ongoing Access)

FULL DATA ACCESS: All administrative data, survey data, qualitative transcripts

USE: Contribution analysis; mechanism testing; assumption examination

CONTRIBUTION ANALYSIS INTEGRATION

The monitoring system is explicitly designed to support contribution analysis by:

Testing Mechanisms

COM-B indicators directly test whether expected causal pathways operate

If capability + opportunity + motivation increase AND behavior changes, mechanism validated

If capability increases but behavior does not, mechanism blocked - need to investigate

Examining Dose-Response

Attendance data linked to outcomes

Expect: Higher attendance → better capability → more behavior change → stronger developmental gains

If no dose-response, challenges contribution claim

Assessing Timeline Consistency

Expect sequence: Capability first (Month 5) → Behavior change (Month 9) → Child outcomes (Month 12-24)

If outcomes appear before capability, suggests alternative explanation

Identifying Assumption Violations

Each critical assumption has monitoring indicator

Example: If attendance \<70%, Assumption 1 violated - informs interpretation of weak results

Ruling Out Alternatives

Comparison group data helps assess secular trends

Baseline balance checks assess selection bias

Mechanism specificity (not generic improvements) challenges Hawthorne effects

Triangulating Evidence

Quantitative surveys + qualitative insights + administrative data + observations

Convergence across sources strengthens contribution claim

Contradictions require explanation

This monitoring system transforms data collection from compliance exercise into contribution analysis foundation. Every indicator serves a purpose - not just \"did we do it\" but \"did it work as expected, and how do we know?\"